EVNest

Weekly Demo & Milestone Checklist

For your weekly review with the developer — pay each milestone only when every box is ticked

Outreach kit  ·  October 2026

## Every week (20–30 minutes)

- Demo on a real Android phone, not a simulator — the developer shows, you tap.

- What was finished, what is blocked, what questions need your answer (answer within 24 hours).

- Check the week against the plan (Document 03 §8). If behind, agree which “can slip” item to drop — never tests.

- Anything built that is not in the documents? It goes back on the “later” list.

### Quick rule checks

- ☐ All code pushed to your GitHub this week.

- ☐ Database changes are migration files in supabase/migrations (not edited by hand in the dashboard).

- ☐ No business rules in the app code: the app calls database functions and shows the result.

- ☐ Names match Document 04 (statuses, functions, error codes).

## Milestone acceptance

### M1 — end of week 1: foundations and login

- ☐ Firebase phone login works and Supabase recognises the user (or the fallback is decided).

- ☐ All tables, enums and constraints from Document 04 §4–5 exist as migrations.

- ☐ Seed data loads a demo society, admin, residents and chargers.

- ☐ On a phone: consent → society code → details → vehicle → Pending approval screen.

### M2 — end of week 3: chargers and sessions

- ☐ Admin can approve, reject and suspend residents in the Admin tab.

- ☐ Admin can add a charger by scanning its QR on site; condition can be changed.

- ☐ Resident scans the QR, picks a duration, checks in; End session works; history shows used time.

- ☐ Day/night limits are correct for the examples in Document 04 §6.

- ☐ Tests pass for start_session and end_session error codes.

### M3 — end of week 4: queue and notifications

- ☐ Two phones: join queue → charger freed → “your turn” push → scan → session starts.

- ☐ Missed turn passes to the next flat; leave queue works; one place per flat enforced.

- ☐ Push arrives with the phone locked; notification list in app matches.

- ☐ Concurrency test: 20 parallel check-ins on one charger → exactly one session.

### M4 — end of week 6: limits, still occupied, admin

- ☐ Reminders at expected end, at limit and while overdue; quiet hours hold pushes and offers.

- ☐ Overdue shows “C2 overdue by N min” to residents; only admin sees the flat.

- ☐ “Still occupied” pauses the turn; clear, give up and admin resolve all work.

- ☐ Auto-close after the limit; missed-turn alert to admin after 3 in 7 days.

- ☐ Admin: end session, queue view, reports, usage log, settings. Account deletion works.

- ☐ All pgTAP tests and the job double-run test pass.

### M5 — end of week 7: pilot ready

- ☐ Every pilot charger set up on site and tested end to end.

- ☐ Play Store internal-testing build installed by at least 3 residents.

- ☐ Privacy policy link and consent text in place.

- ☐ Resident guide and charger posters ready.

- ☐ Code, migrations and a short setup README in your GitHub; you can log in to every account without the developer.